## GSM Cutover Plan
Task ID | Phase | Responsibility | External Dependencies | Activities
GSM-PC-01 | Pre-Cutover | GSM Project Team | Platform team provisioned PROD environment; upstream teams provided configuration values | - Verify all required environment variables are present in PROD - Verify Azure DevOps Library variable groups are linked - Verify Key Vault references resolve successfully - Verify application configuration files are present - Verify no missing or unresolved configuration values - No configuration changes performed
GSM-PC-02 | Pre-Cutover | GSM Project Team / Kafka Team | Kafka team created topics and granted permissions | - Verify Kafka topics exist: TS.SE.DEAL.INTERNAL-(env), TS.SE.OPERATIONAL.EVENT.ETRM.EVENT-(env) - Verify acknowledgement topic exists - Verify GSM producer permissions - Verify consumer group gsm.volume.acknowledgement-prod - Confirm no business messages published
GSM-PC-03 | Pre-Cutover | PRM / Data Team | PRM pipelines completed and populated base data | - Verify Unity Catalog <UNITY_CATALOG_NAME> - Verify base views populated: enriched_deal.vw_base_deal, enriched_gas_physical_position.vw_base, enriched_gas_physical_position.vw_bucketed_base, enriched_etrm_reference.vw_eod_max_completed_portfolio_job, enriched_etrm_reference.vw_eod_undisc_max_completed_portfolio_job - Verify GSM managed identity read access
GSM-PC-04 | Pre-Cutover | GSM Project Team / Data Team | PRM base views populated; GSM curated pipelines deployed | - Verify curated schema curated_gas_storage_management - Verify curated views populated: gsm_vdm_endur_intraday_daily_vols_vw, gsm_vdm_endur_intraday_hourly_vols_vw, gsm_vdm_endur_eod_daily_vols_vw, gsm_vdm_endur_eod_hourly_vols_vw, gsm_vdm_endur_unrestricted_daily_vols_vw, gsm_vdm_endur_unrestricted_hourly_vols_vw - Confirm data lineage from PRM base views
GSM-PC-05 | Pre-Cutover | SAP MTS Team / GSM Project Team | SAP MTS system available and files shared | - Verify SAP MTS SFTP path <SAP_MTS_SFTP_PATH> exists - Verify expected MTS files are present - Confirm file naming and structure - No ingestion enabled
GSM-PC-06 | Pre-Cutover | GSM Project Team | Kafka, PRM, SAP dependencies verified | - Deploy Infrastructure pipeline <INFRA_PIPELINE_NAME> - Deploy GSM API pipeline <GSM_API_PIPELINE_NAME> - Deploy GSM UI pipeline <GSM_UI_PIPELINE_NAME> - Deploy Azure Functions and WebJobs - Confirm services remain disabled
GSM-CW-01 | Cutover Weekend | GSM Project Team | Cutover approval received; upstream systems stable | - Enable GSM Azure Functions <GSM_FUNCTION_APP_NAME> - Enable GSM WebJobs <GSM_WEBJOB_NAMES> - Enable Kafka producers and consumers - Enable scheduled processing
GSM-CW-02 | Cutover Weekend | GSM Project Team | GSM services enabled | - Verify GSM UI loads at <GSM_UI_URL> - Verify key pages - Verify API health endpoint <GSM_API_HEALTH_ENDPOINT>
GSM-CW-03 | Cutover Weekend | GSM Project Team | Kafka topics and permissions verified | - Verify Kafka producer startup - Verify consumer subscription to acknowledgement topic - Verify acknowledgement processing - Monitor logs for errors
GSM-PCOM-01 | Post-Cutover | Business / GSM Project Team | Cutover technically confirmed | - Communicate successful GSM cutover to users - Confirm GSM is live - Share support channels