This document defines Azure DevOps Modules and Product Backlog Items (PBIs) for GSM Cutover Activity List.

# Module 16 – GSM Pre-Cutover Readiness

## [GSM][ADA] Module 16.1 – Pre-Cutover Environment and Configuration Readiness

Description

Verify PROD environment readiness for GSM cutover by confirming environment variables, Azure DevOps Library variable groups, Azure Dev ops pipiline, service connections, and Key Vault references are correctly set up and resolvable. Internal application configuration is validated via standard pipelines and is not itemised.

Acceptance Criteria

Required environment variables for GSM are present in Azure dev ops PROD Library

Azure DevOps Library variable groups are correctly linked

Azure DevOps Pipiline are correctly configured

Key Vault references resolve successfully

Pipeline service connections and permissions authorised

Evidence captured for readiness confirmation

Tasks

Verify environment variables for GSM components

Verify Library variable group linkage for PROD pipelines

Validate Key Vault references resolve successfully

Validate pipeline permissions and service connections

Capture readiness evidence

## [GSM][ADA] Module 16.2 – Kafka Client Identity, Topic Access, and Permissions Readiness

Description

Ensure Kafka identity and permissions required by GSM are established in PROD. No business messages are published during verification.

Acceptance Criteria

Kafka Client ID and Identity Pool ID available

Access granted to required Kafka topics

Consumer group `gsm.volume.acknowledgement-prod` registered with Topic

Producer and consumer permissions confirmed

Tasks

Raise DP ServiceNow request for Kafka Client ID and Identity Pool ID

Obtain access for Topics for Identity Pool, Consumr Group

Raise request to add developemnt team to Identoty Pool

Confirm producer publish permission

Confirm consumer read and offset commit permission

Validate consumer group registration access

Capture evidence

## [GSM][ADA] Module 16.3 – Databricks SQL Warehouse and Managed Identity Access Readiness

Description

Create GSM-owned Databricks SQL Warehouses and ensure GSM managed identity is created and granted Unity Catalog access to query TRM / PRM views in PROD.

Acceptance Criteria

GSM managed identity exists in PROD

Unity Catalog access granted for required schemas and views

Databricks SQL Warehouses created (standard and frequent)

Warehouse IDs captured for configuration

Managed identity can query required views

Tasks

Raise ServiceNow request to create/confirm GSM managed identity

Raise ServiceNow request to grant Unity Catalog access

Track ServiceNow approvals

Create Databricks SQL Warehouse for standard workloads

Create Databricks SQL Warehouse for frequent/intraday workloads

Capture Warehouse IDs

Validate managed identity connectivity

Execute validation queries and capture evidence

## [GSM][ADA] Module 16.4 – TRM Base Views and Data Availability Confirmation

Description

Confirm required TRM views exist and are populated in PROD.

Acceptance Criteria

Required  views exist and are queryable

Data populated by Migration processes

Read access validated for GSM identities

Evidence captured

Tasks

Coordinate with TRM team

Verify view existence

Validate sample data presence

Validate read access

Capture evidence

## [GSM][ADA] Module 16.5 – Portfolio Strategy View Readiness

Description

Confirm portfolio strategy view availability, data freshness, and access.

Acceptance Criteria

portfolio_strategy view exists in PROD

Latest strategy data available

Job schedule confirmed (07:00 UK)

Read access validated

Tasks

Request Guy/Srini to create those View for Prod

Verify view existence

Validate data freshness

Confirm job scheduling and variables

Capture evidence

## [GSM][ADA] Module 16.6 – MTS Interface Readiness

Description

Confirm MTS files required for GSM are available via SFTP.

Acceptance Criteria

SFTP path exists

Expected files present

File naming and structure confirmed

Tasks

Confirm SFTP details

Verify file availability

Validate naming and structure

Capture evidence

## [GSM][ADA] Module 16.8 – Deployment Governance and SOM Approval Gates

Description

Ensure quality gates and approval gates are configured for PROD deployments.

Acceptance Criteria

Quality gates configured

Approval gates configured for Infra, API, UI

Approver groups validated

SOM sign-off obtained

Tasks

Coordinate with SOM

Configure quality and approval gates

Validate approvals

Capture evidence

## [GSM][ADA] Module 16.9 – Pre-Cutover Deployment (Services Disabled)

Description

Deploy GSM components to PROD without enabling services.

Acceptance Criteria

Infrastructure, API, UI deployed successfully

Functions and WebJobs deployed

Services remain disabled

Tasks

Deploy Infrastructure pipeline

Deploy API pipeline

Deploy UI pipeline

Validate deployments

Confirm services remain disabled

## [GSM][ADA] Module 16.10 – Contract Setup in GSM

Description

Create and configure GSM contracts aligned with ETRM migration.

Acceptance Criteria

All in-scope contracts created

Contract configuration validated

Alignment with migrated ETRM data confirmed

Tasks

Identify contracts in scope

Create contracts in GSM via confiurable SQL scripts

craete scripts for flowpoints, capacities, WGV, decline curves, deal mappings

Validate contracts

Capture sign-off

## [GSM][ADA] Module 16.11 – User Migration and Role / Permission Setup

Description

Migrate users and assign roles and permissions in GSM.

Acceptance Criteria

Users created in GSM

Roles and permissions assigned

Access enforcement validated

Tasks

Identify legacy users

Create users in GSM via configurable sql script

Assign roles and permissions

Validate access behaviour

Document access process

## [GSM][ADA] Module 16.12 – Application Access Enablement (Shell Access Management)

Description

Enable GSM access via Shell access management tooling.

Acceptance Criteria

GSM onboarded into access management

Access policies configured

User access validated

Tasks

Raise onboarding request

Configure access policies

Validate authorised and unauthorised access

Capture evidence

## [GSM][ADA] Module 16.13 – WAF Enablement (Pre-Go-Live ?)

Description

Confirm and enable WAF for GSM UI if required.

Acceptance Criteria

WAF requirement confirmed

WAF enabled if mandatory

No valid traffic blocked

Tasks

Confirm requirement

Request WAF enablement

Validate traffic and logs

## [GSM][ADA] Module 16.14 – Operational Readiness and SOM Handover

Description

Complete operational handover to SOM prior to cutover.

Acceptance Criteria

Knowledge transfer completed

Runbooks shared

Escalation paths agreed

SOM readiness confirmed

Tasks

Deliver KT sessions

Share runbooks

Capture readiness confirmation

# Module 17 – GSM Cutover Execution

## [GSM][ADA] Module 17.1 – Service Enablement During Cutover Window

Description

Enable GSM services during the agreed cutover window.

Acceptance Criteria

Functions, WebJobs, Kafka enabled

Enablement performed only during cutover

Tasks

Enable Functions

Enable WebJobs

Enable Kafka processing

Capture evidence

## [GSM][ADA] Module 17.2 – Post-Enablement Smoke Testing

Description

Validate GSM stability post-enablement.

Acceptance Criteria

UI available

Services running without critical errors

Kafka stable

Tasks

UI smoke tests

Validate Functions and WebJobs

Validate Kafka producer and consumer

Review logs

## [GSM][ADA] Module 17.3 – Cutover Go / No-Go Confirmation

Description

Confirm cutover outcome and rollback decision.

Acceptance Criteria

End-to-end validation complete

Go / No-Go decision recorded

Tasks

Review validation results

Record decision

Execute rollback if required

# Module 18 – GSM Post-Cutover Hypercare

## [GSM][ADA] Module 18.1 – Hypercare and User Communication

Description

Provide hypercare support and communicate GSM go-live.

Acceptance Criteria

Hypercare active

Users informed

SOM providing operational support

Tasks

Monitor services

Support SOM

Send go-live communication